## Slide 1: Staffing Methodology Review . NSWPPA Update
7 September 2018

## Slide 2
Our vision is to provide students with a world class education. To do so we need a staffing methodology that ensures every NSW government school has the staffing resources needed to improve student outcomes. This requires a transparent, efficient, flexible and effective system that gets the right people, in the right place, at the right time.
Executive summary
The Staffing Methodology Review commenced in March 2018. To date we have: established a project team, set-up a governance structure, undertaken benchmarking analysis and commenced interviews with stakeholder groups.
The benchmarking analysis has investigated 17 systems across Australia and internationally. We are currently consolidating those insights.
Interviews have recently commenced with a range of internal and external stakeholders to understand strengths and issues in our system. In response to our invitation, NSWPPA has provided a list of 18 schools for us to contact. We are in the process of arranging those meetings.
The project will be led by a Project Control Group comprising Peter Riordan, Georgina Harrisson and Murat Dizdar, and will seek advice from the School Leadership Strategy Steering Committee in addition to other existing reference groups.

## Slide 3
Staffing Methodology Review overview
1. Key issue
Ensuring every NSW government school has the right staffing resources needed to improve student outcomes. That means a system that is better able to get the right people, in the right places, at the right time.
3. Final decision makers
Minister; Secretary (and Executive team).
4. Key stakeholders
 Principals and school staff
 EDs and Directors across DoE
 PPA and SPC
 NSW Teachers Federation
 PSA
 P&C Federation
 AECG
 DPC
 Treasury
 NESA
5. Governance
 Project Control Group being established (repurposing of GTIL PCG) to oversee a cluster of Executive Priority Programs. Members include Dep Sec CS, Dep Sec ES, Dep Sec SOaP.
 PCG report in to DoE Executive Team and provides updates to the School Leadership Strategy Steering Committee.
6. In scope
1. Staffing entitlement – the formula, process and allocation of staff.
2. Staffing system – the methods of appointment.
3. Staffing arrangements – optimisation of demand and supply across system.
7. Key outcomes
 Every NSW government school has the right staffing resources to improve student outcomes.
8. Timings
Adopting a phased approach: Define phase (to Dec 2018), Ideation phase (to Mar 2019), Assess phase (to Jun 2019), Develop phase (to Sept 2019), implementation (from Oct 2019)
9. Program of work
 Benchmarking (Aug 2018)
 Interviews with stakeholders underway – due to complete mid Oct.
2. Context
 We have not had a comprehensive review of staffing in schools for a very long time. Following the introduction of Local Schools Local Decision reforms, it is critical that we now look at this.
 The School Leadership Strategy, announced by the Minister in September 2017, included a commitment to undertake a review of the staffing methodology in schools in 2018.
 Options report back (Apr 2019)
 Assessment report back (Jun 2019)
 Validation report back (Aug 2019)
 Implementation Plan (Oct 2019)

## Slide 4
Program of work
PCG
Exec
MO
Output
Engagement
Updates
Understanding issues & developing criteria
Generating options
Assessing options
Refine & test
Monthly
8 weekly
8 weekly
Benchmarking
Issues Identified
Fact Pack
Scope
Set
Criteria
Set
Options Generated
Assessment report back
Validation
report back
Implementation Plan
Options
report back
benchmarking, Issues, options
I = Interviews
W
I
W = Workshop
I
W
I
W
I
Options Assessed
Today
Discovery
Define
Ideate
Assess
Develop
Implement
Understand issues
Develop criteria
Set scope
Generate options
Assess
Select
Refine
Test
Plan
Pilot

## Slide 5
A range of systems have been selected for benchmarking
  Ontario
  Tennessee
  Washington DC
  Finland
  Singapore
  South Korea
  KIPP
Strong absolute performance and/or significant growth in last decade, based on standardised testing
  Victoria
  Western Australia
  Queensland
  South Australia
Context similarities to NSW
  Tailoring to schools types
    England
    Abu Dhabi
    Goodstart Early Learning
  Optimising demand & supply
    Northern Territory Education
    NSW Health
    NSW Police
Innovative approaches
Notes: Advice on NSW Police?

## Slide 6
Stakeholder interviews
Who we’re interviewing
Corporate Services
Local Schools Local Decisions
Learning & High Performance
School Operations & Performance
Educational Services
EXAR
CESE
EPMO
EPAC
Learning & Business Systems
Industrial Relations
Learning & Wellbeing
Aboriginal Education
Corporate
Schools
External
Executive Directors, School Performance
Directors Educational Leadership (later stage)
Principals (selection TBC)
NSWPPA
NSWSPC
NSW Teachers Federation
PSA
Minister’s Office
Treasury
DPC
AECG
NESA
P&C Federation
In response to our invitation, NSWPPA has provided a list of 18 schools to contact.
We are in the process of setting-up meetings with these school.

## Slide 7
Stakeholder interviews
Interview questions
1. What do you see are the main issues with the current staffing methodology for schools?
2. If there were 3 things you could fix, what would they be, and why?
3. What do you see are the key strengths to preserve of the current system?
4. What do you think are the biggest risks of implementing a new approach?
5. Who else do you think needs to be interviewed or involved?
6. Is there anything else we should be aware of?
We are currently interviewing stakeholders to gain a better understanding of issues with the current system. Interviews will be complete by mid October, with a workshop planned for mid November.

## Slide 8
Back in Term 4
for a more detailed update……..